## Slide 1
PIP-II Project – Linac Overview
Michael Geelhoed, Deputy L2 Manager LI&C
3rd Workshop on Particle Accelerator Upgrade - Removal and Installation
March 2024
FERMILAB-SLIDES-24-0046-AD-PIP2

## Slide 2: Outline
Complex & Mission
Linac Installation Scope
Hardware Process
Installation Planning & Coordination
Enclosure Configuration
1970/2012
1970/1993
1970
1999
1982

## Slide 3: Main Injector
PIP-II
Booster
Transfer Line
SRF Linac
PIP-II will provide a highly capable, reliable, upgradeable and expandable scientific infrastructure with significant savings to DOE

## Slide 4: PIP-II Mission
PIP-II Capabilities
Beam Power
1.2 MW proton beam
Upgradeable to multi-MW
Flexibility, multi-user capability
CW-compatible
Customized beams
Multi-user delivery
Reliability
Modernizes Fermilab accel complex
PIP-II is an essential upgrade to Fermilab accelerator complex to enable the world’s most intense beam of neutrinos to LBNF/DUNE, and a broad physics research program for decades to come.
PIP-II Scope
800 MeV H− SRF linac CW RF Operations
Linac-to-Booster transfer line Accelerator Complex Upgrades
Booster Recycler Main Injector
Conventional Facilities
Space reserved for two CMs for 1 GeV Upgrade
The PIP-II scope enables the accelerator complex to reach 1.2 MW proton beam on LBNF target

## Slide 5: Superconducting Linac
Notes: From Source to last HB 650 CM slot ~ 250 meters

## Slide 6: Key Performance Parameters
# | Scope | Threshold KPPs | Objective KPPs
1 | Linac Beam Energy | Accelerate H- beam to 600 MeV | Accelerate H- beam to 700 MeV Linac systems required to accelerate beam to 800 MeV installed and tested
2 | Linac Beam Intensity | Beam delivered to Beam Dump at the end of Linac | Beam with intensity of 1.3E12 particles per pulse (H-) at 20 Hz delivered to Beam Line Dump
3 | Booster/ Recycler/ Main Injector upgrades | Booster, Recycler, and Main Injector Upgrades to support operations with beam power of 1.2 MW on the LBNF target are installed and tested without beam | Linac beam injected and circulated in Booster
Objective KPPs are aligned with the baseline project scope. However, the normal operating beam parameters:
  800 MeV
  20 Hz
  <2 mA>
4.97E17 particles/hr 17.6 kW

## Slide 7: PIP-II Project Management and L2 Systems and Managers

## Slide 8: Linac Installation and Commissioning
C. Baffes
M. Geelhoed*
121.04.05
Linac Installation
Support Equipment
Installation Planning
D
D. Lambert
PIP2IT Disassembly, Cryomodule Storage
D
Linac Installation
R. Ridgway
Cryomodule Stands
C. Baffes
CTTS
K. Kendziora
Warm Unit Structures
K. Kendziora
Installation Tools
M. Simon
CDS Access Platform
K. Kendziora
HBB Shield Door
T. Hamerla
CAD
A. Bujak
Installation Traveler Development
M. Simon
Installation Procurement Planning
M. Geelhoed
Verification & Validation Lead
V. Bocean
Alignment Network
K. Kendziora
Warm Unit Integration
C. Baffes
WFE/SCL Installation Engineering Lead
D. Lambert
WFE/SCL Installation Technical Lead

## Slide 9: Linac Installation Scope
Booster
Beam Transfer Line (BTL)
BTL
F37 Service Building
HighBay Building (HBB)
Linac Gallery
Linac Tunnel
Cryoplant
LI Team Installs Accelerator Equipment
Existing Main
Ring
Accelerator Upgrades Installation Geographic Scope
LI Installation Scope
  All Linac cryomodules
  All Solid-State Amplifiers
  Beamline Equipment
  Power supplies
  Instrumentation
  Controls

## Slide 10: Linac Installation – 3D CAD Model
Integrated 3D CAD model being used to manage design for all of PIP-II
Not-to-exceed envelopes established as guidelines for system designs
  Allows for parallel progress and interface verification between systems at different levels of design maturity

## Slide 11: Linac Installation – 3D CAD Model
Integrated 3D CAD model being used to manage design for all of PIP-II
Not-to-exceed envelopes established as guidelines for system designs
  Allows for parallel progress and interface verification between systems at different levels of design maturity
Final Linac Complex CF model has been integrated
Integrates design geometry from multiple sources
  FNAL, Partners, CF/AE, lattice

## Slide 12: Linac Installation – 3D CAD Model
Integrated 3D CAD model being used to manage design for all of PIP-II
Not-to-exceed envelopes established as guidelines for system designs
  Allows for parallel progress and interface verification between systems at different levels of design maturity
Final Linac Complex CF model has been integrated
Integrates design geometry from multiple sources
  FNAL, Partners, CF/AE, lattice
Integrated detailed models

## Slide 13: Linac Installation – 3D CAD Model
Integrated 3D CAD model being used to manage design for all of PIP-II
Not-to-exceed envelopes established as guidelines for system designs
  Allows for parallel progress and interface verification between systems at different levels of design maturity
Final Linac Complex CF model has been integrated
Integrates design geometry from multiple sources
  FNAL, Partners, CF/AE, lattice

## Slide 14: Hardware Process
Partner or vendor delivery
L3 Testing and QC
L3 acceptance of partner/vendor deliverable
per Acceptance Criteria Document and List
L3-managed documentation stored in Fermilab systems (procedures, drawings, travelers, QC data, etc.)
Handoff to installation WBS
Hardware gets configured shipment/delivery by L3
Installation Readiness Review, administered by Tech. Integration
Fail
Pass
Partner/Vendor Documentation (procedures, drawings, travelers, QC data, etc.)
Partner
L3
Tech. Int.
Installation
Responsibility
Installation Deliverable List Document
Hardware gets configured by L3 as agreed per Installation Deliverable List
LI team input:
tensioned process

## Slide 15: Hardware Process (cont)
L3
Handoff to installation WBS
Hardware gets configured shipment/delivery by L3
Installation
Operational Readiness Clearance
Conditioning
Installation to Commissioning Handoff Review
Accelerator Readiness Review
Beam Commissioning
Transition to Operations
Accelerator Complex Operations
Beam Comm
Installation
Responsibility
Acc Complex

## Slide 16: Hardware Process (cont)
Partner
L3 Manager
Linac Installation
Beam Commissioning
Accelerator Complex
Tech Integration
Design, Fabrication, Production
Commission
Installation

## Slide 17: Installation Planning and Coordination
A. Bujak

## Slide 18: Installation Planning and Coordination
FY
Linac Installation &

## Slide 19: Installation Planning and Coordination

## Slide 20: Enclosure Access Classifications
Open Access
  Areas fully open to trained personnel
  Only possible if residual radiation hazards are absent
Supervised Access
  Interlocks dropped
  Keys issued to each entrant
  Power supplies are locked off
  Access requires a clear, planned break in operations
Controlled Access
  Interlocks remain active, specific access procedures required to keep them made up
  Keys issued to each entrant
  Power Supplies remain off
  Allows for access coupled with operations

## Slide 21: Enclosure Access Classifications
Oxygen Deficiency Hazard
  ODH 0: Low hazard, few restrictions on entry
  OHD 1: Training, qualification, and PPE required for entry
    Supervised Access mode can be used to verify training and manage access
SCL Enclosure will be classified as ODH 1 after the Cryogenic Distribution System is charged
Other Enclosures have barriers and/or sufficient ventilation to maintain ODH 0 status at all times

## Slide 22: Enclosure Access Transitions
AUG-2027→
NOV - 2027→
JAN - 2028→
3 CMs in
before transition
6 CMs in
before transition
10 CMs in
before transition
A. Bujak

## Slide 23
THE FUTURE OF FERMILAB
Follow us:
http://pip2.fnal.gov/
@PIP2accelerator
/showcase/pip-ii/
geelhoed@fnal.gov